## Product Backlog
POC3-Blog project | [6 empty] | Story point estimation
# | REQ ID | Features/Requirements-Level1 | Features/Requirements-Level 2 | ReleasePhase/Milestone | Priority | Status | Initial estimation | Sprint
[7 empty] | 0 | 1
[7 empty] | 118 | 118
Application Management/Administration
1 | REQ01 | Landing Page
|  |  | US_01-Header and Footer | Release 1 | P1 | Completed | 5 | 5
|  |  | US_02-Featured Tab | Release 1 | P1 | Completed | 8 | 8
|  |  | US_03-Top Highlights | Release 1 | P1 | Completed | 13 | 13
|  |  | US_04-Recent Posts | Release 1 | P1 | Completed | 3 | 3
|  |  | US_05-Sponsored News | Release 1 | P1 | Completed | 3 | 3
2 | REQ02 | Detail Page
|  |  | US_06-Post Description | Release 1 | P2 | Completed | 13 | 13
|  |  | US_07-Related Posts | Release 1 | P3 | Completed | 3 | 3
|  |  | US_08-Comments Section | Release 1 | P3 | Completed | 13 | 13
3 | REQ03 | Admin Login Page
|  |  | US_09-Login Form | Release 1 | P2 | Completed | 21 | 21
4 | REQ04 | CRUD Functionality
|  |  | US_10-Create post | Release 1 | P1 | Completed | 13 | 13
|  |  | US_11-Update Post | Release 1 | P2 | Completed | 5 | 5
|  |  | US_12-Delete Post | Release 1 | P2 | Completed | 5 | 5
5 | REQ05 | Post List
|  |  | US_13-Display Post List | Release 1 | P2 | Completed | 5 | 5
|  |  | US_14-Pagination, Sorting, Searching | Release 1 | P3 | Completed | 8 | 8

## Sprint Backlog
Sprint Backlog
ID | Requirement | Tasks | Owner | Status | Estimated Effort | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
US_01 | Header and Footer | US_01_T1 - Header Layout | Shruti | Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | US_01_T2- Footer Layout | Shruti | Completed | 4 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0
|  | US_01_T3- Hamburger Menu | Shruti | Completed | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0
US_02 | Featured Tab | US_02_T1- Featured Tab Layout | Ramya | Completed | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
|  | US_02_T2- Dynamic rendering of Featured Tab | Ramya | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0
US_03 | Top Highlights | US_03_T1- Top Highlights Layout | Ramya | Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
|  | US_03_T2- Top Highlights Dynamic rendering | Ramya | Completed | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
|  | US_03_T3- Load More Layout | Shruti | Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
|  | US_03_T4- Load More Functionality | Shruti | Completed | 6 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0
US_04 | Recent Post | US_04_T1- Recent Posts Layout | Ramya | Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
|  | US_04_T2- Recent Posts Dynamic Rendering | Ramya | Completed | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
US_05 | Sponsored News | US_05_T1- Sponsored News Layout | Ramya | Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
|  | US_05_T2- Sponsored News Rendering | Ramya | Completed | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
US_06 | Main Post Description | US_06_T1 - Post Description Layout | Srusti | Completed | 8 | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0
|  | US_06_T2-Dynamic Rendering of Post Description | Srusti | Completed | 6 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
US_07 | Comments Section | US_07_T1- Comment Section layout | Srusti | Completed | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | US_07_T2- Add Comments | Srusti | Completed | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  | US_07_T3- Delete Comments | Srusti | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  | US_07_T4- Existing Comments | Srusti | Completed | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1
US_08 | Related Posts Section | US_08_T1- Related Posts | Srusti | Completed | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
US_09 | Admin Login | US_09_T1- Login and Logout Form Layout | Shruti | Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
|  | US_09_T2-Login and logout functionality | Shruti | Completed | 8 | 0 | 0 | 2 | 3 | 2 | 1 | 0 | 0
|  | US_09_T3-Manual Routing to other admin pages | Shruti | Completed | 6 | 0 | 0 | 0 | 1 | 3 | 2 | 0 | 0
US_10 | Posts Listing Table | US_10_T1-Post List Layout | Supreet | Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | US_10_T2-Pagination | Supreet | Completed | 3 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0
|  | US_10_T3-Sorting functionality | Supreet | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | US_10_T4-Searching functionality | Supreet | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
US_11 | Posts Creation | US_11_T1-Create Post/Edit Post UI Layout | Ramya | Completed | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0
|  | US_11_T2-Update Local Stoarge with new posts | Supreet | Completed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
US_12 | Posts Read | US_12_T1-Displaying posts data from localstorage | Supreet | Completed | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0
US_13 | Posts Updation | US_13_T1-Fetching exsiting data from local storage | Supreet | Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  | US_13_T2-Updating changes to local storage | Supreet | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2
US_14 | Posts Deletion | US_14_T1-Delete Posts | Supreet | Completed | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0

## Burn Down Chart
Time |  | Tasks Remaining
Day | Dates | Planned | Actual
Tue | Day 0 | 33 | 33
Wed | Day 1 | 28 | 30
Thu | Day 2 | 23 | 25
Fri | Day 3 | 18 | 18
Mon | Day 4 | 13 | 12
Tue | Day 5 | 9 | 6
Wed | Day 6 | 4 | 3
Thu | Day 7 | 0 | 0

## Retrospective
Project Name : Blog Application
Sprint-1.0 |  | Date: 04-Jan-2024
# | +ve | ∆ | Action Item | Target Date | Responsible
1 | 98% Tasks are getting completed on time or before time | The code was being modified by another team member | Code conflicts to be resolved by informing the author of the code | Next Project | Team
2 | Team Coordination and communication is very good | Git should be handled with more clarity | Clarity in comments while committing the codes | Next Project | Team
3 | Research done effectively on new technologies and implemented |  |  |  | Team
4 | Cross browser testing has been completed and tested |  |  |  | Team
5 | Workload was equally balanced among all team members |  |  |  | Team
∆